## Sheet1
Task | Event | Anticipated Start Date | Anticipated Completion/Submittal Date
Removal Bagged Waste | Excavation | 2016-08-15 | 2016-09-02
| Lab Results Available | - | 2016-10-07
| Completion Report Submittal | - | 2016-10-21
Remedial Action Plan | Remedial Action Plan Submittal | - | 2016-09-01
Monitoring Well Network | Well Installation | 2016-08-22 | 2016-09-30
| Sampling | 2016-09-05 | 2016-10-28
| Lab Results Available | - | 2016-11-11
Groundwater Management Permit Application | Application Submittal | - | 2016-12-02
Source Remediation | System Construction | 2016-09-26 | 2016-12-23
| System Startup | - | 2017-01-03
| As-Built Submittal | - | 2017-01-27
| Remedial Completion Report Submittal | - | 2017-04-28